## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DT-0006_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1519 |  |  | Transmital Date: 19 Oct 2022
Document Title: Data Sheets For Control/Regulator valves - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1519 |  |  | Transmital Date: 19 Oct 2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-DT-0006_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اختلاف و نهایی نشدن سایز ها در مرحله تفصیلی ، میبایست سایزهای مندرج در مدارک پیمان ملاک عمل قرار گیرد. |  | 01/2294/283397 | 1401/08/06 | سایز شیر مطابق توافقات درج شد. محاسبات و صحه گذاری نهایی توسط سازندگان انجام خواهد شد.
2 | در خصوص متریال اعلام شده تطابق مشخصات با PMS تاییدشده الزامی است. |  | 01/2294/283397 | 1401/08/06 | توضیحات لازم مطابق توافقات اضافه شد.لازم به ذکر است متریال ذکر شده برای Trimمطابق Spec ابزار دقیق بالاتر از متریال ذکر شده در PMS است لذا تنها NOTE بدون تغییراضافه شد. در مورد Stellite توضیحات لازم در note6 امده است. متریال خط مطابق PMS اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 1 Nov 2022 |  |  |  |  | Date: