## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-RT-0007-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1510 |  |  | Transmital Date:18-Oct-2022
Document Title: Stress Analysis Calculations Report For Manifold Area |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-1510 |  |  | Transmital Date:18-Oct-2022
[5 empty] | CRS No:NISOC-BK-W007S-PEDCO-110-PI-RT-0007-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در پیوست 10 کتابچه پیمان ذکر گردیده است، ضروریست کلیه محاسبات مربوط به آنالیز تنش مانند: خطوط لوله، انکرها، انکرهای کوهستانی و ... علاوه بر تحلیل نرم افزاری بصورت دستی نیز ارائه گردد. در این راستا ارائه برخی جززیات از جمله: تعاریف نیروهای وارده، برایند نیروی وارد شده بر هر نقطه و ... الزامی است. |  | 01/2294/281069 | 1401/08/03 | احتراما نقطه نظر اعمال گردید
2
3
4
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 29.Oct.2022 |  |  |  |  | Date: 29.Oct.2022