## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-RT-0007-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1510 |  |  | Transmital Date:18-Oct-2022
Document Title: Stress Analysis Calculations Report For Manifold Area |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-1510 |  |  | Transmital Date:18-Oct-2022
[5 empty] | CRS No:PEDCO-BK-W007S-PEDCO-110-PI-RT-0007-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | استانداردها و مدارك مرجع در بخش Reference ذكر گردد. |  | BK-SUR-ENG-PIP-01-06008 | 2022-10-29 | احتراما نقطه نظر اعمال گردید
2 | در نقشه شماتيك مدل ارائه شده شماره نود ها مشخص گردد. |  | BK-SUR-ENG-PIP-01-06008 | 2022-10-29 | احتراما نقطه نظر اعمال گردید
3 | براي كليه نودها فشار و درجه حرارت طراحي و ضخامت لوله ها بايستي بر اساس مدرك PMS لحاظ گردد. |  | BK-SUR-ENG-PIP-01-06008 | 2022-10-29 | احتراما نقطه نظر اعمال گردید
4 | با توجه به اينكه در مدل سه بعدي ساپورتها نمايش داده نشده و نقشه هاي ايزومتريك كه نشان دهنده موقعيت و نوع ساپورتها باشد نيز دريافت نگرديده است در خصوص مدل تحليل تنش ارائه شده نمي توان اظهار نظر قطعي نمود. بهتر است در نقشه شماتيك مدل تحليل تنش موقعيت و نوع ساپورتها مشخص گردد. |  | BK-SUR-ENG-PIP-01-06008 | 2022-10-29 | احتراما نقطه نظر اعمال گردید
5 | آيا خطوط متصل به پمپ تخليه حوضچه درين نياز به تليل تنش ندارد؟ |  | BK-SUR-ENG-PIP-01-06008 | 2022-10-29 | احتراما با توجه به سایز و مشخصات خط و طبق اسپک استرس آنالیز پروژه، خط مذکور نیاز به استرس انالیز ندارد. البته پس از مشخص شدن وندور و مشخصات پمپ، در ویرایش بعدی این خط نیز به دفترچه محاسبات اضافه خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 29.Oct.2022 |  |  |  |  | Date: 29.Oct.2022