## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK12-PEDCO-110-CV-RT-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1548 |  |  | Transmital Date: 25-OCT-2022
Document Title: Site Visit Report (Civil Work) - BK12 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1548 |  |  | Transmital Date: 25-OCT-2022
[5 empty] | CRS No: NISOC-CRS-BK-BK12-PEDCO-110-CV-RT-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مبنای مساحت 2560 مترمربعی مندرج در گزارش چیست. شفاف گردد. |  | 01/2294/296556 | 1401/08/14 | منظور مساحت نهایی پد بتنی (64*40) است. جهت جلوگیری از ابهام عبارت یاد شده حذف شد.
2 | موارد مندرج در بند 6 گزارش (جمع بندی) ارتباطی با محتوای گزارش و جمع بندی مورد نیاز ندارد. تکرار موارد مندرج در شرح کار پیوست 10 در گزارش، موضوعیت ندارد. حذف گردد. |  | 01/2294/296556 | 1401/08/14 | حذف شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: