## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-SP-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1264 |  |  | Transmital Date: 8/10/2022
Document Title: Duty Specification for Instrument/Plant Air & Nitrogen Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1264 |  |  | Transmital Date: 8/10/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-SP-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | كامنت پيشين: اعداد عنوان شده در خصوص ميزان نقطه شبنم و نيز قطر ذرات با مدرك Basis of Design مطابقت ندارد. |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | اصلاح گردید.
2 | حداكثر ميزان روغن مجاز مي بايست از صفحه 10 حذف و به بخش كمپرسور( صفحه 9 ) اضافه گردد. |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | اعمال ‌گردید.
3 | نوت نوشته شده در انتهاي بند 4.1.2.3 مي بايست حذف گردد. |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | اعمال ‌گردید.
4 | جمع جبري آيتم هاي 4.1.2.1 با تك تك موارد مطابقت ندارد |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | اصلاح گردید.
5 | در آيتم 3.3 صرفا به دياگرام هاي مرتبط اشاره گردد. |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | اصلاح گردید.
6 | در بخش گارانتي هواي ابزاردقيق، ميزان دماي خروجي نيز ذكر گردد. |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | اصلاح گردید.
7 | نهايي سازي ميزان و مشخصات مورد نياز نيتروژن، پس از دريافت اطلاعات سازنده كمپرسور گاز امكان پذير خواهد بود. |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | مورد تایید است.
8 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05519 | 2022-08-24 | اعمال می‌گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: