## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PR-DT-0030 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1444 |  |  | Transmital Date: 10/1/2022
Document Title:Process Data Sheets For Gas Compressors Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1444 |  |  | Transmital Date: 10/1/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0030_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقطه نظر پیشین: در اين مدرك محاسبه Settling Out Pressure بر عهده سازنده گذاشته شده است كه با توجه به عدم دسترسي سازنده به اطلاعات مورد نياز و نيز ارتباط آن با طراحي صورت گرفته توسط پيمانكار، لازم است در اين مقطع موارد تكميل گردد و پاسخ ارائه شده در Replysheet، قابل قبول نمی باشد. |  | BK-SUR-ENG-PCS-01-05886 | 2022-10-12 | اعمال گردید.
2 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05886 | 2022-10-12 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021

## Sheet2
2021-11-07