## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0013_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1286 |  |  | Transmital Date: Aug-20th-2022
Document Title: CCCTV Equipment Layout Inside CCTV Control Room in Binak GCS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0105-IN-TR-1286 |  |  | Transmital Date: Aug-20th-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-PY-0013 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | متریال و نوع دربها و پنجره های ساختمان ها ارائه گردد. |  | 1401-2294-205790 | 1401-06-10 | همانطور که مستحضر هستید، مرجع اول این مدرک، نقشه معماری ساختمان CCTV می باشد. در صورت درج متریال و نوع درب و پنجره ساختمان، هرگونه تغییر در مدرک معماری تغییر در این مدرک را ایجاد میکند. لذا جهت تفکیک وابستگی مدارک از یکدیگر خواهشمند است برای مشاهده نوع درب و پنجره و . . . به همان مرجع اول مراجعه گردد.
2 | مکان نصب پنل داخلی و بیرونی آیفون تصویری در مدرک ارائه گردد. |  | 1401-2294-205790 | 1401-06-10 | مکان نصب پنل داخلی و بیرونی آیفون تصویری در مدرک ارائه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: AP.Golrang | Signature |  |  |  | Clarified By: | Signature
| Date: Aug-27th-2022 |  |  |  |  | Date: