## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-AR-DW-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1347 |  |  | Transmital Date:9/3/2022
Document Title: Architectural Drawing For Chemical Inj. Packages/Chemical Storage Shelter |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0004-AR-T-1347 |  |  | Transmital Date: 9/3/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0004_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | سازه ی CHEMICAL INJ. PACKAGES/CHEMICAL STORAGE SHELTER دارای سه دهانه بوده است. (دو دهانه پکیج تزریق و یک دهانه انبار، در حالیکه طرح ارسالی با دو دهانه می باشد.) |  | 1401-2294-227958 | 1401/06/27 | با توجه به سه دهانه برای سایبان پکیج و مواد شیمیایی در طرح بیسیک ( یک هانه برای پکیج CORROSION INHIBITOR، یک دهانه برای METHANOL و یک دهانه برای ذخیره بشکه های مواد شیمیایی) و اینکه در مطالعات مهندسی ارزش یک پکیج متانول (و بالتبع سایبان مربوطه) حذف گردیده است، و از طرفی بشکه های ذخیره مواد شیمیایی محدود به ماده ضد خوردگی شده،و در نتیجه فضای کمتری نیاز دارد،لذا سایبان موردنظر دارای دو دهانه ( یک دهانه برای پکیج CORROSION INHIBITOR و یک دهانه برای ذخیره بشکه های ماده ضد خوردگی) خواهد بود.
2 | در جلسه ی بررسی مدل سه بعدی مورخ 1401/03/22 مقرر گردید آن پیمانکار، با جابه جایی SLUG CATCHER DRUM، و افزایش یک دهانه دیگر،نسبت به تامین فضای بارانداز کامیون اقدام نماید. |  | 1401-2294-227958 | 1401/06/27
3 | پیرو بند بالا، و در امتداد محل STORAGE (به سمت شرق)، یک دهانه خالی روباز برای ورود کامیون با امکان پوشش با جرثقیل سقفی،مهیا گردد که هیچیک از گفته های فوق دیده نمی شود. |  | 1401-2294-227958 | 1401/06/27
4 | نقاط مختصاتی و رقوم ارتفاعی در این مدرک لحاظ نشده است. |  | 1401-2294-227958 | 1401/06/27 | اعمال شد.
5 | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
6
7 | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
8 | Commented By: | Signature |  |  |  | Clarified By: | Signature
9
10 | Date: |  |  |  |  | Date:
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
Legend
Signature