## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document NoBK-W035-PEDCO-110-IN-TB-000_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0539 |  |  | Transmital Date: 2 Feb 2022
Document Title: TBE/TBA For Instrument Bulk Items - W008 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0008-IN-TR-0539 |  |  | Transmital Date: 2 Feb 2022
[5 empty] | CRS No: NISOC-CRSBK-W008-PEDCO-110-IN-TB-000_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | باتوجه اینکه مدارک فوق جهت ارزیابی دو مدرک TBE for instrument cable tray و TBE for Instrument Tube& Fitting برای هر چاه محل میباشد و تنها فقط برای قسمت اول (TBE For Cable Tray) جدول ارزیابی ارسال شده است و برای قسمت دوم ( TBE for Instrument Tube & Fitting) جدول ارزیابی وجود ندارد ( بعلت معرفی تنها یک شرکت) ، لذا ترانسمیتال ارسالی عودت میگردد. لازم است برای هر دو قسمت مدرک حداقل پیشنهاد ازسه شرکت سازنده/تامین کننده مجاز و از لیست AVL وزارت نفت ( ارائه مدارک مثبته حضور در لیست AVL همراه با پیشنهاد فنی) ارائه گردد. |  | 00/2294/443275 | 1400/12/19 | مدرک مطابق خواست کارفرمای محترم اصلاح و به روز رسانی شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 14 Feb 2022 |  |  |  |  | Date: