## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No BK-W046S-PEDCO-110-IN-TB-000_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0539 |  |  | Transmital Date: 2 Feb 2022
Document Title: TBE/TBA For Instrument Bulk Items - W045 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0008-IN-TR-0539 |  |  | Transmital Date: 2 Feb 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W046S-PEDCO-110-IN-TB-000_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه وضعیت مدرک IFIو بند 13 پیمان, مسئولیت تمامی موارد در این مدرک (مالی و زمانی) بر عهده پیمانکار می باشد. |  | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | ملاحظه شد.
2 | با توجه به اینکه مدارک پیش نیاز این مدرک نهایی نشده است و دارای کامنت می باشد, چنانچه هر گونه تغییری در مدارک مرتبط ایجاد شود, مدرک مربوطه باید به روز رسانی گردد. |  | BK-SUR-ENG-INS-00-03068 | 2022-02-14 | مطابق آخرین تغییرات در پیشنهادات سازندگان به روزرسانی شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 14 Feb 2022 |  |  |  |  | Date: