## NISOC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
pedec
Document No: BK-GCS-PEDCO-120-IN-LI-0009_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1066 |  |  | Transmital Date: 12 Jun 2022
Document Title: Instrument /F&G Cable List |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1066 |  |  | Transmital Date: 12 Jun 2022
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0009_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص موارد REPLY SHEET نظر خاصی مطرح نمی باشد |  | 01/2294/171118 | 1401/05/18 | -
2 | این مدرک با توجه به تغییرات مدارک مرجع بروز رسانی گردد |  | 01/2294/171118 | 1401/05/18 | مدرک حاضر با توجه به تغییرات مدارک رفرنس اصلاح گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 22 Jun 2022 |  |  |  |  | Date: