## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PI-SP-0007-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0039 |  |  | Transmital Date: 09-Aug.-2021
Document Title: SPECIFICATION FOR LINING ( INTERNAL PROTECTION OF EQUIPMENT BY PAINTING) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0039 |  |  | Transmital Date:09-Aug.-2021
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0007-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بخش مراجع استانداردهای NORSOK M501، ISO 21809-3، ISO16961 افزوده گردد. |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرما ی محترم اعمال می گردد. استاندارد ISO 21809-3 مربوط به خطوط لوله بوده و مربوط به مخازن نمی باشد.
2 | با توجه به اینکه مدرک در مرحله تفصیلی می باشد لازم است سامانه رنگ مطابق با تجهیزات موجود در پروژه با ذکر شماره مخزن ظروف تعیین شود. لذا جدول رنگ مطابق با مواد اعلام شده اصلاح و ظروفی که در پروژه کاربرد ندارند از مدرک حذف گردد. |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرما ی محترم اعمال می گردد. باتوجه به اینکه سیستم های پوششی شماره دارند و این شماره ها قبلا در دیتاشیت های مربوطه وارد شده و مورد تایید قرار گرفته اند.، با حذف پوشش های غیر ضروری ترتیب این شماره ها به هم میخورد، لذا حذف نشدند.
3 | در جدول سامانه های رنگ برای مخزن/ظروف تحت فشار علاوه بر دما، فشار عملیاتی نیز مد نظر قرار گیرد. |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرما ی محترم اعمال می گردد.
4 | لزوم ارزیابی سامانه کالای رنگ مطابق با استاندارد مرجع در آزمایشگاه ثالث مورد تایید کارفرما قبل از شروع به کار پروژه و مطابق با itp تایید شده تحت نظارت نماینده این امور در مدرک ذکر گردد. |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرما ی محترم اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:05-Sep.-2021 |  |  |  |  | Date: 05-Sep.-2021