## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PI-SP-0008-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0039 |  |  | Transmital Date: 09-Aug.-2021
Document Title: Specification For Material Requirements in Sour service |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0039 |  |  | Transmital Date:09-Aug.-2021
[5 empty] | CRS No:NISOC-CRS-BK-GNRAL-PEDCO-000-PI-SP-0008-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | برای لوله های مورد استفاده در محیط ترش درصد ترکیب شیمیایی می بایست بر اساس جدول H.1 استاندارد API 5L اصلاح گردد. |  | 01/2294/156748 | 1401/05/05 | این مشخصات فنی صرفا برای لوله نمی باشد و ترکیب شیمیایی ذکر شده برای لوله های غیر API 5l می باشد. برای لوله های API 5L که در این پروژه مختص خطوط لوله می باشند در مدرک ذکر شده است که ترکیب شیمیایی مطابق IPS-M-PI-190 یا همان API 5L می باشند..
2 | پذیرش عیوب برای آزمون های غیر مخرب ورق و لوله می بایست بر اساس جدول K1 استاندارد IPS-M-PL_190 در نظر گرفته شود که در مدرک ASTM A578-LEVEL A در نظر گرفته شده است. |  | 01/2294/156748 | 1401/05/05 | این مشخصات فنی صرفا برای لوله نمی باشد. برای لوله های API 5L جدول K.1 در نظر گرفته می شود.
3 | عدم انجام آزمون HIC برای لوله های بدون درز می بایست برر اساس شرایط سیال و ارزیابی ریسک آن صورت پذیرد. |  | 01/2294/156748 | 1401/05/05 | در شرایط با ریسک بالا نظیر خطوط لوله مطابق IPSتست انجام می شود.
4 | در بند 5.3 مدرک نوع گواهینامه کالا می بایست EN102024-3.2 در نظر گرفته شود. |  | 01/2294/156748 | 1401/05/05 | نقطه نظر کارفرمای محترم اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:05-Sep.-2021 |  |  |  |  | Date: 05-Sep.-2021