## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PI-SP-0011-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0039 |  |  | Transmital Date: 09-Aug.-2021
Document Title: SPECIFICATION FOR WELDING OF PLANT PIPING SYSTEM & NDT |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0039 |  |  | Transmital Date:09-Aug.-2021
[5 empty] | CRS No: NISOCCRS-BK-GNRAL-PEDCO-000-PI-SP-0011-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بند 6.2.1.6 اضافه شده در مدرک رسایی کامل ندارد و می بایست اصلاح گردد. |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرمای محترم اعمال گردید.
2 | برند الکترود به طور ویژه برای الکترودهای ایرانی یک پارامتر اساسی در نظر گرفته شود. |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرمای محترم اعمال گردید.
3 | در مدرک ذکر گردد الکترودها تنها دوبار می توانند بازپخت شوند و اگر الکترودی بعد از 4 ساعت از باز پخت دوم مورد استفاده قرار نگیرد دور ریخته می شود. |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرمای محترم اعمال گردید.
4 | تمام روش های انجام آزمون های غیر مخرب می بایست به تایید یک بازرس غیر مخرب با سطح 3 برسند. |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرمای محترم اعمال گردید.
5 | بند 11.6 استاندارد IPS متناظر با مدرک برای شرایطی که دو جوشکار در ایجاد عیب سهیم می باشند نیز در نظر گرفته شود. |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرمای محترم اعمال گردید.
6 | تعیین مینیمم ضخامت 12.7 میلیمیتر جهت عدم انجام عملیات حرارتی PWHT در محیط های ترش به تنهایی نمی تواند کافی باشد. در روش جوشکاری سختی سنجی و همچنین متالوگرافی جهت تعیین میکرو ساختار هم در ناحیه HAZ و هم فلز جوش می بایست جهت نهایی سازی تصمیم در ااین خصوص در نظر گرفته شود چرا که علاوه بر کاهش سختی کاهش تنشهای پسماند و تمپر کردن مارتنزیت های موجود در میکرو ساختار از اهداف تنش زدایی می باشند/ |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:05-Sep.-2021 |  |  |  |  | Date: 05-Sep.-2021