## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PI-SP-0015-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0039 |  |  | Transmital Date: 09-Aug.-2021
Document Title: SPECIFICATION FOR PIPING CONSTRUCTION, FABRICATION & ERECTION |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0039 |  |  | Transmital Date: 09-Aug.-2021
[5 empty] | CRS No: CRS-BK-GNRAL-PEDCO-000-PI-SP-0015-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | برای سیستم لوله کشی فرآیندی زیر زمینی مدفون نمودن لوله مدنظر نمی باشد.. لذا استفاده از پل به همراه نقاط تخلیه و پوشش دهی خارجی(پوشش های مایع بدون حلال) مد نظر قرار گیرد. در صورت مدفون نمودن پوشش و سامانه حفاظت کاتدی ضروری می باشد. |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرمای محترم اعمال می گردد.
2 | به منظور تعویض ادوات پایش خوردگی بوسیله Retriver نیاز به فضای مناسب و همچنین دسترسی می باشد. لذا این امر در سامانه لوله کشی مد نظر قرار گیرد. |  | 1401-2294-156748 | 1401/05/05 | نقطه نظر کارفرمای محترم اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:05-Sep.-2021 |  |  |  |  | Date: 05-Sep.-2021