## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GNRAL-PEDCO-000-PI-SP-0002-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0677 |  |  | Transmital Date: 06-Mar-2022
Document Title: Specification For Transportation, Handling, Storage of pipes |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-0677 |  |  | Transmital Date: 06-Mar-2022
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0002-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه در پروژه خط لوله 8 اينچ گاز از لوله هاي داراي External Coating استفاده مي شود مدرك بايستي در بر گيرنده لوله هاي مذكور نيز باشد. لذا در مدرك علاوه بر اينكه Scope اصلاح مي گردد بايستي در خصوص لوله هاي حاوي پوشش خارجي نيز مطالبي اضافه گردد. |  | BK-SUR-ENG-PIP-00-03538 | 2022-03-14 | در استاندارد IPS-M-PI-140 برای لوله های پوشش شده نیز الزاماتی مطرح شده شده است. لذا اسکوپ بر این مبنا ویرایش گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:13-Mar-2022 |  |  |  |  | Date:13-Mar-2022