## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-000-PI-SP-0015-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0039 |  |  | Transmital Date: 09-Aug.-2021
Document Title: SPECIFICATION FOR PIPING CONSTRUCTION, FABRICATION & ERECTION |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0039 |  |  | Transmital Date: 09-Aug.-2021
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-000-PI-SP-0015-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 2.3 مدرك زير اضافه شود BK-SSGRL-PEDCO-320-PI-SP-0007 SPECIFICATION FOR LINING INTERNAL PROTECTION OF EQUIPMENT BY PAINTING ) |  | BK-SUR-ENG-PIP-00-01462 | 05-Sep.-2021 | این مشخصات فنی مربوط به پایپینگ می باشد و در پایپینگ Lining نداریم.
2 | بك بندي تحت عنوان Bending and Forming اضافه شود و توضيحات لازم نوشته شود |  | BK-SUR-ENG-PIP-00-01462 | 05-Sep.-2021 | اعمال گردید.
3 | با توجه به اينكه LINING در پروژه وجود دارد لذا بند 13 مربوط به LINING به مدرك اضافه شده و توضيحات لازم نوشنه شود |  | BK-SUR-ENG-PIP-00-01462 | 05-Sep.-2021 | این مشخصات فنی مربوط به پایپینگ می باشد و در پایپینگ Lining نداریم.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date:05-Sep.-2021 |  |  |  |  | Date: 05-Sep.-2021