## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GNRAL-PEDCO-000-PI-SP-0017-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0350 |  |  | Transmital Date:15-Dec-2021
Document Title: Specification For Cleaning and Flushing |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-0350 |  |  | Transmital Date:15-Dec-2021
[5 empty] | CRS No:CRS-BK-GNRAL-PEDCO-000-PI-SP-0017-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بخش 3.2 كلمه Pipelines از عنوان ذكر شده براي استاندارد ASME B31.3 حذف گردد. در اين برهه نقطه نظر خاصی مطرح نمی باشد .از اين رو پيشبرد گام بعدی مهندسی بلامانع است. شايان ذکر است با توجه به مفاد 13 شرايط عمومی پيمان, مسئوليت هر نوع نقص و کمبود در نقشه ها و مدارک فنی در محدوده پروژه و در هر مقطع از پروژه بر عهده پيمانکار است. |  | BK-SUR-ENG-PIP-00-02374 | 2021-12-19 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: J.Mousazadeh | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 19-Dec-2021 |  |  |  |  | Date: 19-Dec-2021