## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PR-LI-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0848 |  |  | Transmital Date: 4/20/2022
Document Title: Tie-In List - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0848 |  |  | Transmital Date: 4/20/2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-PR-LI-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به تغییر میزان برش آب مخازن آسماری و بنگستان میدان بینک مطابق نامه شماره 1401/2294/8112 مورخ 1401/01/15 مقتضی است کلیه مدارک مرتبط بازنگری و تصحیحات لازم صورت پذیرد . |  | 1401-2294-70086 | 1401/02/31 | اعمال گردید.
2 | همچنین به منظور رعایت تقدم و تاخر در بررسی مدارک می بایست مدارک PFD , P&ID ضمن اعمال نقطه نظرات قبلی (نامه های شماره 1401/2294/43153 تاریخ 1401/02/06 و 1401/2294/52764 تاریخ 1401/02/18 و 1401/2294/59523 تاریخ 1401/02/22 ) ، جهت بررسی و اظهار نظر همزمان و یا قبل از مدرک فوق مجددا ارائه گردد. |  | 1401-2294-70086 | 1401/02/31 | مدارک ذکر شده با آخرین ویرایش ارسال شده است. و این مدرک نیز طبق همان اصلاحات ، ارسال می گردد.
3 | فشار طراحی (Design Pressure) ارائه شده برای کلاس 300(102 بار گیج) صحیح نمی باشد و. لازم به ذکر است فشار طراحی می بایست بالاتر از حداکثر فشار عملیاتی (MOP) و کمتر از فشار مجاز کاری (MAWP )، که حدود 50 بار گیج می باشد ، در نظر گرفته شود . |  | 1401-2294-70086 | 1401/02/31 | اعمال گردید .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: