## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PR-LI-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0848 |  |  | Transmital Date: 4/20/2022
Document Title: Tie-In List - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0848 |  |  | Transmital Date: 4/20/2022
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-PR-LI-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقاط اتصال معرفي شده با واقعيت فعلي واحد و مدل سه بعدي انجانم شده آن پيمانكار مغاير بوده و لازم است بانگري كلي در اين خصوص هم در اين مدرك و هم در P&ID مربوطه صورت پذيرد. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | اصلاح گردید .
2 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-04314 | 2022-05-21 | اعمال گردید .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: