## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-DG-0003_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1049 | Transmital Date: 7 Jun 2022
Document Title: Instrument Hook-up Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1049 | Transmital Date: 7 Jun 2022
[5 empty] | CRS No: NISCO-CRS-BK-W007S-PEDCO-110-IN-DG-0003_D00 | CRS Status:
Item |  |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) | Client Conclusion
1 | مدارک زیر نیز بعنوان مرجع در نظر گرفته شوند: *Instrument & Control System Desing Criteria *Specification For Instrumantation *Specification For Control Valves * Specification For On-off/Shut Down Valves (ESDV/MOC) - *TYPICAL INSTRUMENT INST ALL ATION DRAWING |  | 1401-2294-201845 | 1401/06/08 | اضافه گردید.
2 | تجهیزات با توجه به نقشه های P & ID بروزرسانی و علائم بدون کاربرد حذف گردد. ( صفحه 5) در همین صفحه توضیحی برای عنوان صفحه قید گردد. |  | 1401-2294-201845 | 1401/06/08 | حذف گردید.
3 | سیال فرآیندی گاز نمی باشد، مطابق SPEC و دیتاشیت ، این مدرک با توجه به نوع سیال، مورد بازنگری قرار گیرد. |  | 1401-2294-201845 | 1401/06/08 | با توجه به نوع سیال اصلاح شد.
4
5