## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-CV-PY-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1343 |  |  | Transmital Date: 31-AUG-2022
Document Title: Civil Layout For LBV Stations |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1343 |  |  | Transmital Date: 31-AUG-2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-CV-PY-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | جهت باد غالب مشخص گردد. |  | 01-2294-285895 | 1401/08/08 | اعمال شد.
2 | یک درب خروج اضطراری در طرف مقابل درب لحاظ شده پیش بینی شود |  | 01-2294-285895 | 1401/08/08 | اعمال شد.
3 | مقتضی است Grade Level تعیین شود |  | 01-2294-285895 | 1401/08/08 | اعمال شد.
4 | محل فونداسیون Anchor Blocks خط لوله مزبور در پیش و بعد از فنس، جانمایی و نمایش داده شود. |  | 01-2294-285895 | 1401/08/08 | اعمال شد.
5 | محل پلت فرمهای دسترسی به LBV ترسیم گردد. |  | 01-2294-285895 | 1401/08/08 | این مورد بعد از نهایی شدن وندور و جزئیات مورد نیاز جهت تعیین ابعاد و ارتفاع پلتفرم مشخص می گردد و در مدرک Plot Plan دیده خواهد شد.
6 | در مسیر FloodWay مقتضی است محل سازه های مورد لزوم جانمایی و نمایش داده شود. |  | 01-2294-285895 | 1401/08/08 | اعمال شد.
7 | در Legend نقشه نشانه تعریف شود |  | 01-2294-285895 | 1401/08/08 | اعمال شد.
| یادآوری می گردد تعداد ایستگاهها و مختصات LBV مطابق با اسناد پیمان مدنظر این امور می باشد. بنابراین آن پیمانکار در صورت وجود هرگونه مغایرت، موضوع را اطلاع رسانی نماید. بدیهی است که این مهم بر عهده شرکت پتروایران می باشد. |  | 01-2294-285895 | 1401/08/08 | تعداد ایستگاهها و مختصات LBV مطابق با اسناد پیمان است. جانمایی LBV موجود و LBV جدید (بر اساس اسناد پیمان) و فاصله بین آنها در تصویر زیر نشان داده شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: