## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PI-DG-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0934 |  |  | Transmital Date: 11.May.2022
Document Title: Material Flow Diagram - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0934 |  |  | Transmital Date: 11.May.2022
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-PI-DG-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بازگشت به نامه شماره BK-PEDCO-NISOC-0102-PI-LT-3678 مورخ 1401/02/21 سیستمی به اطلاع می رساند مدارک این ترانسمیتال پس از نهایی شدن مدارک خوردگی و انتخاب مواد، جنس و حد مجاز خوردگی تجهیزات و سیستم لوله کشی معین خواهد شد. از این رو خاطر نشان می گردد، ضروری است ضمن رعایت اولویت بندی در ارسال مدارک ، نسبت به نهایی نمودن مدارک پیش نیاز مبادرت گردد. |  | 01/2294/124157 | 1401/04/09 | مورد تایید است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021