## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-DG-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-934 |  |  | Transmital Date: 11.May.2022
Document Title: Material flow Diagram |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-0934 |  |  | Transmital Date: 11.May.2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PI-DG-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | Material Flow Diagram shall be in accordance with final approved Piping corrosion study and Material Selection Report for GCS. |  | BK-SUR-ENG-PIP-01-04380 | 23.May.2022 | Corrosion study and Material Selection Report for GCS has been submitted.
2 | Material Flow Diagrams shall be in accordance with final P&ID's by identifying size and rating of all Valves, reducers and Equipment (if any). It is better to identify all Instruments, too. |  | BK-SUR-ENG-PIP-01-04380 | 23.May.2022 | This document revised based on last revision of PFD.
3 | The document Piping corrosion study and Material Selection Report BK-GCS-PEDCO-120-PI-RT-0001 shall be referred. All P&ID's of GCS shall be referred, too |  | BK-SUR-ENG-PIP-01-04380 | 23.May.2022 | Noted.
4 | Note 1 shall be added as follows: 1- WALL THICKNESS SHALL BE IN ACCORDANCE WITH WALL THICKNESS CALCULATION REPORT. |  | BK-SUR-ENG-PIP-01-04380 | 23.May.2022 | Noted.
5 | The material and Corrosion Allowance shall be specified for 4" Condensate Pipeline |  | BK-SUR-ENG-PIP-01-04380 | 23.May.2022 | According to calculations material should be C.S. + 6mm Corrosion allowance NACE. Relevant calculation will be presented in the next revision of Manifold corrosion study. This line exists and material selection is informative.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021