## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-IN-DG-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1198 |  |  | Transmital Date: 26 Jul 2022
Document Title: Instrument Hook-up Diagram - Wellheads |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1198 |  |  | Transmital Date: 26 Jul 2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-IN-DG-0001_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrument Comments
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05392 | 2022-08-09 | ملاحظه و بررسی گردید.
2 | با توجه به كامنت 2 مدرك پيشين، مورد NACE درج گردد. لازم به ذكر است كه اين كامنت در مدرك MTO نيز ديده شده است. |  | BK-SUR-ENG-INS-01-05392 | 2022-08-09 | در MTO ی صفحه ای 4، این آیتم 1 و 128 جدا گردیده است.
Piping Comments
4 | . با توجه به اينكه CC و CP در مدرك فوق ذكر نشده است بررسي گردد كه در صورت لزوم به مدرك اضافه شود. |  | BK-SUR-ENG-INS-01-05392 | 2022-08-09 | در P&ID به CC /Cp اشاره نشده است.
Process Comments
5 | در صفحه 6 (PG) شير ايزوله در بخش ابزار دقيق مي بايست در جدول مربوطه گنجانده شود. |  | BK-SUR-ENG-INS-01-05392 | 2022-08-09 | شیر ایزوله در MTO ابزاردقیق آورده نمی شود . در این مدرک اصلاح گردید .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 9 Aug 2022 |  |  |  |  | Date: