## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DT-0002_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0888 |  |  | Transmital Date: 01 May 2022
Document Title: Data Sheets For Temperature Gauge |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0888 |  |  | Transmital Date: 01 May 2022
[5 empty] | CRS No: PEDCO-CRS-BK-PPL-PEDCO-320-IN-DT-0002_D01 |  |  | CRS Status: | C3
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
Instrumentation Comments
1 | مسئوليت تعداد و انواع ادوات ابزار دقيق بر عهده پيمانكار مي باشد. |  | BK-SUR-ENG-INS-01-04313 | 2022-05-18 | ملاحظه شد.
2 | با توجه به نهايي نبودن مدارك پيش نياز مانند P&ID، در صورت تغييرات موارد در مدرك نيز اعمال گردد. |  | BK-SUR-ENG-INS-01-04313 | 2022-05-18 | اعمال گردید.
3 | Range بايد Design Tempreture را كاور كند. |  | BK-SUR-ENG-INS-01-04313 | 2022-05-18 | رنج design tempurature را در نظر میگیرد.
Process Comments
4 | در جدول صفحه 6 ميزان Viscosity مشخص گردد. |  | BK-SUR-ENG-INS-01-04313 | 2022-05-18 | اضافه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 18 May 2022 |  |  |  |  | Date: