## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-CV-PY-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1497 |  |  | Transmital Date: 15 OCT 2022
Document Title: Rough Grading Plans -BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1497 |  |  | Transmital Date: 15 OCT 2022
[5 empty] | CRS No: NISOC-CRS-BK-BK14-PEDCO-110-CV-PY-0003-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیرو تذکرات پیشین به دلیل اینکه تاکنون مدارک و مستندات مربوط به Civil Layout نهایی سازی نشده اند امکان اظهار نظر صحیح در خصوص R.G این چاه محل و در این مرحله مقدور نمی باشد. |  | 01-2294-296585 | 1401/8/14 | نهایی سازی مدارک پیش نیاز گاهاً زمانبر می باشد که این پیمانکار برای کاهش تاخیر در روند مهندسی و ساخت پروژه ، در بعضی موارد مدارک مورد نیاز ساخت را به صورت موازی با هم ارسال می نماید ، خواهشمند است آن کارفرمای محترم نیز برای تسهیل روند پروژه و تسریع در روند ساخت ، نسبت به بررسی مدارک اقدام نمایند. شایان ذکر است که تمامی تغییرات احتمالی در مدارک پیش نیاز بصورت توامان اعمال خواهد گردید.
2 | جدول احجام Cut/Fill Volume از مدرک حذف گردد. |  | 01-2294-296585 | 1401/8/14 | اعمال گردید.
3 | مدرک plot plan مصوب ارائه شود مقتضی است این مهم برای تمامی چاه محل های دارای تلمبه های یدک انجام پذیرفته و مدرک مذبور به لیست مدارک پروژه افزوده گردد. |  | 01-2294-296585 | 1401/8/14 | در مدارک پایپینگ یک Sketch برای نشان دادن تجهیزات مورد نیاز و بصورت تیپیک برای چاهها نشان داده شده بود که محل جانمایی ها صحیح نبود. در مرحله تفصیلی و با توجه به مسیر هوایی انتقال برق ، موقعیت ساختمانها و درب ورودی مشخص شده است؛ که چاه به چاه متفاوت می باشد وبراساس این موقعیت ها ادوات و ساختمانهای مورد نیاز نیز جانمایی می گردند که غالبا مغایر با جانمایی اسناد پایه می باشد.
4 | پس از اصلاح و انجام نکته های فوق این مدرک دوباره با P.O.I.=IFC تهیه و ارسال گردد. |  | 01-2294-296585 | 1401/8/14 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: