## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-CV-DW-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1511 |  |  | Transmital Date: 10/18/2022
Document Title: Civil and Structural drawings - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1511 |  |  | Transmital Date: 10/18/2022
[5 empty] | CRS No: NISOC-CRS-BK-BK14-PEDCO-110-CV-DW-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-2294-296566 | 1401/08/14 | . در مدارک پایپینگ یک Sketch برای نشان دادن تجهیزات مورد نیاز و بصورت تیپیک برای چاهها نشان داده شده بود که محل جانمایی ها صحیح نبود. در مرحله تفصیلی و با توجه به مسیر هوایی انتقال برق ، موقعیت ساختمانها و درب ورودی مشخص شده است که چاه به چاه متفاوت می باشد وبراساس این موقعیت ها ادوات و ساختمانهای مورد نیاز نیز جانمایی می گردند که غالبا مغایر با جانمایی اسناد پایه می باشد.
2 |  |  | 1401-2294-296566 | 1401/08/14 | مدارک جداگانه ای برای هر کدام از ساختمانها و شلتر وجود دارد که در لیست مدارک رفرنس درج گردید
3 |  |  | 1401-2294-296566 | 1401/08/14 | مقاطع مشخص شده در شیت 2 مشخص می باشد
4 |  |  | 1401-2294-296566 | 1401/08/14 | در لیست مدارک رفرنس اضافه گردید.
5 |  |  | 1401-2294-296566 | 1401/08/14 | میلگرد گذاری محل هایی که بتن آن تخریب نمی شود اصلاح گردید. لیستوفر بعد از تایید نقشه در ویرایش بعدی ارائه میگردد
6 |  |  | 1401-2294-296566 | 1401/08/14 | جمله مذکور اصلاح گردید
7 |  |  | 1401-2294-296566 | 1401/08/14 | برروی دیوار پلاستر سیمانی لحاظ گردید
8 |  |  | 1401-2294-296566 | 1401/08/14 | با توجه به نیازمندیهای بخش حفاری ، محدوده گودالهای موجود با جداساز به دو گودال Waste Pit و Cutting Disposal جهت تامین نیازمندیهای مدیریت پسماند تقسیم شده است.
9 |  |  | 1401-2294-296566 | 1401/08/14 | اصلاح شد.
10 |  |  | 1401-2294-296566 | 1401/08/14 | اعمال شد
11 |  |  | 1401-2294-296566 | 1401/08/14 | اعمال شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: