## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK12-PEDCO-110-EL-MR-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1152 |  |  | Transmital Date: 13-Jul-2022
Document Title: PMR For Transformers - BK12 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0104-EL-TR-1152 |  |  | Transmital Date: 13-Jul-2022
[5 empty] | CRS No: PEDCO-CRS-BK-BK12-PEDCO-110-EL-MR-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
EL Comments
1 | Use attched sample MR for nex revision. (Following documents shall be added to sample MR as general document): -Packing, Marking, Transportation Procedure -Document Numbering Procedure -Electrical Load List of Well Pads -دستورالعمل جامع بازرسی خرید و ساخت کالا -دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات |  | BK-SUR-ENG-ELE-01-05232 | 2022-07-25 | اعمال گردید.
QA/QC Comments
2 | در بند 5.1.1 عبارت QA Organization به QA/QC Organization Chart تغییر یابد. |  | BK-SUR-ENG-ELE-01-05232 | 2022-07-25 | اعمال گردید.
3 | در بند 6: 1-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-ELE-01-05232 | 2022-07-25 | اعمال گردید.
4 | در جدول Attachment 1(List of Reference/Applicable Documents): 1-دستورالعمل FDB Requirements اضافه گردد. 2- -دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. 3-دستورالعمل Packing, Marking, Transportation Procedure اضافه گردد. |  | BK-SUR-ENG-ELE-01-05232 | 2022-07-25 | اعمال گردید.
5 | در جدول Attachments 2 (Vendor Documents Minimum Requirements) : - در رديف 001، عبارت "See Attachment 2" حذف گردد. -SAT Procedure اضافه گردد. -مدارك غير مرتبط حذف گردد. |  | BK-SUR-ENG-ELE-01-05232 | 2022-07-25 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 25-Jul-22 |  |  |  |  | Date: