## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-EL-MT-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1403 |  |  | Transmital Date: 14-Sep-2022
Document Title: MTO For Transmission Over Head Line - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-EL-TR-1403 |  |  | Transmital Date: 14-Sep-2022
[5 empty] | CRS No: PEDCO-CRS-BK-BK14-PEDCO-110-EL-MT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | There is confilict between this document and Over Head Line Plan and Profile-BK14 form point of No. of towers view, it shall be rechecked and modified. |  | BK-SUR-ENG-ELE-01-05771 | 2022-09-28 | اصلاحات لازم در مقادير بر اساس نقشه پلان پروفيل تجديدنظر 02 با كد BK-BK14-PEDCO-110-EL-DW-0001-D02 انجام گرديد.
2 | This document shall be revised after finalizing or minnor commets on Over Head Line Plan and Profile-BK14. |  | BK-SUR-ENG-ELE-01-05771 | 2022-09-28 | ملاحظه گرديد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 28-Sep-22 |  |  |  |  | Date: