## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W008N-PEDCO-110-IN-PY-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1277 |  |  | Transmital Date: 15 Aug 2022
Document Title: Instrument Location Layout Drawing - W008N |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1277 |  |  | Transmital Date: 15 Aug 2022
[5 empty] | CRS No: PEDCO-CRS-BK-W008N-PEDCO-110-IN-PY-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05539 | 2022-08-27 | ملاحظه گردید.
2 | در خصوص لاين return مربوط به SSV شفاف سازي صورت پذيرد. اين مورد بايد مطابق صورتجلسه KOM مربوط به WHCP در مدارك ديده شود. |  | BK-SUR-ENG-INS-01-05539 | 2022-08-27 | در این مدرک خطوط مربوط به SSV/SSSV نمایش داده نشده است تنها Cable Tray مربوط به این خطوط نمایش داده شده است.
3 | مشخص گردد كه sensing line ها به چه صورت به WHCP متصل مي شوند. |  | BK-SUR-ENG-INS-01-05539 | 2022-08-27 | جانمایی Cable Tray , WHCP در این نقشه نمایش داده شده است و نحوه اتصال sensing line ها در مدرک Instrument Hook-up Diagram - Wellheads نمایش داده شده است.
4 | با توجه به مذاكرات شفاهي در خصوص وجود CC و CP، در صورت وجود موارد بايد در اين مدرك ديده شود. |  | BK-SUR-ENG-INS-01-05539 | 2022-08-27 | مطابق P&ID چاه مربوطه ، CC و CP وجود ندارد.
5 | Note 5 در مدرك اضافه گردد. |  | BK-SUR-ENG-INS-01-05539 | 2022-08-27 | Note 5 مربوط به PLOT PLAN چاه می باشد که در پس زمینه این مدرک قرارداده شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 27 Aug 2022 |  |  |  |  | Date: