## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-DG-0001-D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1378 |  |  | Transmital Date: 07-Sep-2022
Document Title: Electrical Typical Schematic Diagrams For LV Panels of Well Pads |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-EL-TR-1378 |  |  | Transmital Date: 07-Sep-2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DG-0001-D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیرو بند 6 از نامه 393495 مورخ 1400/11/13 نمونه ولتاژ ژنراتور می بایست بر روی تابلوی CB2 کلید ورودی ژنراتور به MCC در مجاورت ولتمتر ولتاژ باس نرمال نشان داده شود. (ولت متر آنالوگ مد نظر می باشد.) |  | 1401-2294-249451 | 1401-07-13 | مطابق با بند 13 از صورتجلسه در دفتر آن کارفرمای محترم، مقرر گردید نقشه های شماتیک برای ورودیها و کوپلر از نقشه های طراحی تفصیلی حذف گردد و این مدارک توسط سازنده تهیه گردد. در فاز طراحی فقط نقشه های لاجیک برای این کلیدها تولید خواهد شد. از اینرو یک نوت اضافه گردید که در آن اشاره شده است سازنده می بایست مدارک لاجیک و دیاگرام تک خطی را ملاک خود قرار دهد. بنابر این در مدرک تک خطی نمونه ولتاژ ژنراتور به تابلوی LV جهت نمایش ارسال می گردد.
2 | با توجه به اینکه برخی نکات در مرحله ساخت کالا و بر اساس نحوه ساخت سازنده مربوطه تعیین خواهد شد، لذا سایر موارد در مرحله ساخت کالا و بر روی مدارک سازنده اعلام خواهد شد. |  | 1401-2294-249451 | 1401-07-13 | در زمان نهایی سازی تابلوهای سرچاهی با سازنده، ملاحظات مورد نیاز به ایشان یادآوری خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 21-Sep-22 |  |  |  |  | Date: