## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0005-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0562 |  |  | Transmital Date: 07/Feb/2022
Document Title: PMR For Storage Tanks |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-BK-ME-0012-T-0562 |  |  | Transmital Date: 07/Feb/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0005-D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | از آنجایی که مدارک مهندسی مرتبط تا کنون نهایی نشده اند لذا تولید این مدرک در این مقطع مورد تایید نبوده و قابل بررسی نمی باشد. |  | 00/2294/430776 | 1400/12/10 | با توجه به نهایی شدن مدارک پیوست M.R ، لذا خواهشمند است بررسی مدرک مذکور در دستور کار قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.naserizadeh |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
Date: