## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0005_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0562 |  |  | Transmital Date: 07/Feb/2022
Document Title: PMR FOR STORAGE TANKS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-BK-ME-0012-T-0562 |  |  | Transmital Date: 07/Feb/2022
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-ME-MR-0005 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | please find the attached comments |  | BK-SUR-ENG-MEC-00-03351 | 2022-03-05 | Please find the reply on the attachment.
2 | در بند 6: 1-عبارت "Project ITP Procedure)" به "دستورالعمل بازرسي خريد و ساخت كالا" به شماره مدرك ICE-EID-MI-SP01-Rev.01 تغيير يابد. 2-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-000-00-03256 | 2022-02-27 | 1. نقطه نظر کارفرمای محترم اعمال شد. 2- دستورالعمل مورد نظر در لیست مدارک وجود داشت.
3 | در بند 12.2، در جلسه PIM نمايندگان شركتهاي پترو ايران و NISOC نيز حضور خواهند داشت. |  | BK-SUR-ENG-000-00-03256 | 2022-02-27 | 1. پیرو مذاکرات تلفنی با جناب آقای مهندس باورساد، نقطه نظر شماره 3 مرتفع گردید..
4 | در جدول Attachment 1(List of Reference/Applicable Documents): 1-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV01 اضافه گردد. |  | BK-SUR-ENG-000-00-03256 | 2022-02-27 | 1. دستورالعمل مورد نظر در لیست مدارک وجود داشت.
5 | در جدول Attachments 2 (Vendor Documents Minimum Requirements): 1. در رديف 1، عبارت "See Attachment 2" حذف گردد. 2- عبارت "List of Documents will be Finalized in Vendor Document Index and Schedule" به عنوان نوت اضافه گردد |  | BK-SUR-ENG-000-00-03256 | 2022-02-27 | 1. نقطه نظر کارفرمای محترم اعمال شد. 2- نقطه نظر کارفرمای محترم اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.naserizadeh |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
| Date: 02/27/2022 |  |  |  |  | Date: