## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-PY-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0458 |  |  | Transmital Date:15-Jan-2022
Document Title: Plot Plan Drawing - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-0458 |  |  | Transmital Date:15-Jan-2022
[5 empty] | CRS No:NISOC-CRS-BK-W007S-PEDCO-110-PI-PY-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | محدوده و مسیر خطوط در نقشه جدید نشان داده نشده است لذا امکان بررسی و اظهار نظر در خصوص این مدرک وجود ندارد. |  | 00/2294/395124 | 1400/11/15 | احتراما نقطه نظر اعمال گردید
2 | نحوه نمایش خطوط جدید در بخش LEGEND درج گردد. |  | 00/2294/395124 | 1400/11/15 | احتراما نقطه نظر اعمال گردید
3 | با توجه به اینکه با توسعه فنس کلاستر، عرض مسیر (PATROL ROAD ) دسترسی چاه های بینک 1 و 2 کاهش می یابدعرض مناسب جهت عبور ماشین آلات سنگین تعمیراتی در نظر گرفته شود. |  | 00/2294/395124 | 1400/11/15 | احتراما برای توسعه فنس عرض 5 متری برای Patrol road لحاظ گردید و بر این مبنا فنس جابجا گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri G.Khosravizadegan | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 1400/11/15 |  |  |  |  | Date: 1400/11/15