## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W007S-PEDCO-110-PI-PY-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0458 |  |  | Transmital Date:15-Jan-2022
Document Title: Plot Plan Drawing - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-0458 |  |  | Transmital Date:15-Jan-2022
[5 empty] | CRS No:PEDCO-CRS-BK-W007S-PEDCO-110-PI-PY-0001-D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات بصورت مارك شده در نقشه به پيوست ارسال مي گردد. |  | BK-SUR-ENG-PIP-00-02800 | 2022-01-24 | احتراما پاسخ موارد به پیوست ارسال می گردد
2 | اين نقشه فاقد هرگونه اطلاعات اوليه مورد نياز مي باشد و به لحاظ فني قابل بررسي نمي باشد حداقل اطلاعات مربوط به چيدمان خطوط درون محوطه و بيرون آن - فواصل - رواداريها - نفاط tie-in - شيرآلات و تجهيزات ، پلاتفرم هاي دسترسي و ... مي بايست نمايش داده شود با توجه به اينكه عرض جاده دسترسي كاهش يافته ، آيا گزينه ديگري براي جانمايي منيفولد ورودي در مجاورت محوطه اصلي و اتصال از طريق خط هدر بررسي گرديده است؟ |  | BK-SUR-ENG-PIP-00-02800 | 2022-01-24 | موارد بررسی شده و پس از اخذ تایید کارفرمای محترم فنس جابجا گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri G.Khosravizadegan | Signature |  |  |  | Clarified By: A.Dabiri | Signature
| Date: 24-Jan-2022 |  |  |  |  | Date: 24-Jan-2022