## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK15-PEDCO-110-EL-MR-0005_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1311 |  |  | Transmital Date: 24-Aug-2022
Document Title: PMR For DC Charger - BK15 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0106-EL-TR-1311 |  |  | Transmital Date: 24-Aug-2022
[5 empty] | CRS No: NISOC-CRS-BK-BK15-PEDCO-110-EL-MR-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | لازم است مدرک PMR مربوط به چاه 7 نیز تولید و ارائه گردد. |  | 1401-2294-216127 | 1401-06-17 | با توجه به اینکه شارژر منیفولد و چاه 7 در یک مدرک تولید میشود، لذا پس از نهایی شدن ظرفیت شارژرِ مورد نیازِ منیفولد، مدرک MR تولید خواهد شد.
2 | لازم است دوره آموزشی سیستم شارژر جهت 5 نفر در محل مورد تأیید کارفرما در مدرک لحاظ گردد. |  | 1401-2294-216127 | 1401-06-17 | مطابق با پیوست 12 از اسناد مناقصه پروژه، دوره آموزشی مرتبط با تعمیر و نگهداری در شرح کار این پیمانکار می باشد و انجام خواهد شد. لذا خواهشمند است از لحاظ کردن این موضوع در مدرک MR صرف نظر گردد. چراکه در قرارداد وجود دارد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 05-Sep-22 |  |  |  |  | Date: