## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W035-PEDCO-110-CV-DW-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1381 |  |  | Transmital Date: 11-Sep-22
Document Title: Rough Grading Plans -W035 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1381 |  |  | Transmital Date: 11-Sep-22
[5 empty] | CRS No: NISOC-CRS-BK-W035-PEDCO-110-CV-DW-0001-D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | به اطلاع می‌رساند با عنایت به اینکه تاکنون مدرک General Civil Layout W035 مطابق با نامه شماره 222585 مورخ 1401/6/22 که به دلایل فنی و مهندسی تائید نهایی نشده است، لذا امکان بررسی و اظهار نظر برای این ترانسمیتال وجود ندارد.. |  | 1401-2294-232682 | 1401/06/30 | احتراما مدرک موردنظر نهایی و ارسال گردید. لازم به ذکر است نهایی سازی مدارک پیش نیاز گاهاً زمانبر می باشد که این پیمانکار برای کاهش تاخیر در روند مهندسی و ساخت پروژه ، در بعضی موارد مدارک مورد نیاز ساخت را به صورت موازی با هم ارسال می نماید ، خواهشمند است آن کارفرمای محترم نیز برای تسهیل روند پروژه و تسریع در روند ساخت ، نسبت به بررسی مدارک اقدام نمایند. شایان ذکر است که تمامی تغییرات احتمالی در مدارک پیش نیاز بصورت توامان اعمال خواهد گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date:

## Sheet2
BINAK Oil Field Project Overall Well Location/Facilities Layout | BK-SSGRL-PEDCO-110-CV-PY-0001