## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-CV-DW-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1230 |  |  | Transmital Date: 1-AUG-2022
Document Title: Rough Grading Plans -W046S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1230 |  |  | Transmital Date: 1-AUG-2022
[5 empty] | CRS No: PEDCO-CRS-BK-W046S-PEDCO-110-CV-DW-0001-D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به كامنت هاي قبلي و آنكه جانمايي ابنيه چاه محل- مديريت پسماند مطابق آخرين توافقات با تيم حفاري - كارفرما باشد و در ديگر نقشه هاي مرتبط نيز همخوان با اصلاحات صورت پذيرفته باشد ، نقطه نظر ديگري مطرح نمي باشد |  | BK-SUR-ENG-CIV-01-05573 | 2022-08-31 | جانمایی واحدهای پسماند بر اساس تاییدیه کارفرما انجام شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date:

## Sheet2
BINAK Oil Field Project Overall Well Location/Facilities Layout | BK-SSGRL-PEDCO-110-CV-PY-0001