## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1307 |  |  | Transmital Date: 8/24/2022
Document Title: P&ID - Gas Compression Inlet Knock Out Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1307 |  |  | Transmital Date: 8/24/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | دلیل تغییر نوع شیرهای تخلیه ¾" بر روی نازل S (Utility Connection) و 1 ½” بر روی نازل (Liquid outlet) B2 برای V-2015 از Gate Valve به Ball Valveچیست ؟ ( تغییرات نوع شیر قابل پذیرش نیست در صورت وجود الزام استانداردی توضیحات لازم اراِئه گردد.) |  | 1401-2294-281080 | 1401/08/03 | اصلاح گردید
2 | علت حذف اتصال فلنج RS در جریان PSV خروجی از V-2015 چیست؟ |  | 1401-2294-281080 | 1401/08/03 | اصلاح گردید
3 | دلیل تغییر نوع شیرهای تخلیه ¾” قبل و بعد از شیر LCV-2114 از Gate Valve به Ball Valve چیست؟ ( تغییرات نوع شیر قابل پذیرش نیست ؛ در صورت وجود الزام استانداردی توضیحات لازم ارائه گردد.) |  | 1401-2294-281080 | 1401/08/03 | اصلاح گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: