## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1307 |  |  | Transmital Date: 8/24/2022
Document Title: P&ID - 1st Stage Gas Compression Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1307 |  |  | Transmital Date: 8/24/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | توصیه شماره 40 از مدرک "HAZOP Report for Compressor Station” اعمال شود. |  | 1401-2294-281080 | 1401/08/03 | در آیتم شماره 40 از مدرک "HAZOP Report for Compressor Station” در خصوص Maintenece Lock فن کولر هوایی اشاره شده که می در مدرک Data Sheet مکانیکال تجهیز فوق اعمال می گردد. |  |  | دیسیپلین مکانیک
2 | شماتیک کولر هوایی بایستی بصورت Induced Draft Type Air Cooler نمایش داده شود و شماتیک مربوط به مدرک “ Symbol and Legend for PFD and P&ID" اضافه شود. |  | 1401-2294-281080 | 1401/08/03 | اعمال گردید. |  |  | DRAFTMAN
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: