## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1307 |  |  | Transmital Date: 8/24/2022
Document Title: P&ID - Gas Compression Inlet Gas Pipeline (Golkhari) |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1307 |  |  | Transmital Date: 8/24/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0003_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | HAZOP Recommendation شماره 8، در خصوص حداقل فاصله Purge Connection از Barred Tee در نقشه اعمال نشده است. |  | BK-SUR-ENG-PCS-01-05694 | 2022-09-13 | اعمال گردید.
2 | HAZOP Recommendation شماره 9، در خصوص FB بودن شیر توپی در TIE-IN POINT، در نقشه اعمال نشده است. |  | BK-SUR-ENG-PCS-01-05694 | 2022-09-13 | اعمال گردید.
3 | تاییدیه تغییرات صورت گرفته در شرح کار پیمانکار گلخاری می بایست به صورت نامه رسمی از ذینفع اصلی پروژه اخذ گردد. |  | BK-SUR-ENG-PCS-01-05694 | 2022-09-13 | مورد تایید است
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05694 | 2022-09-13 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021