## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1307 |  |  | Transmital Date: 8/24/2022
Document Title: P&ID - Gas Compression Inlet Knock Out Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1307 |  |  | Transmital Date: 8/24/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0005_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقطه نظر پیشین: نهايي سازي خطوط فلر منوط به ارسال محاسبات قابل قبول مي باشد.( مفاد صورتجلسه مورخ 1401/06/19 در این خصوص مد نظر قرار گیرد) |  | BK-SUR-ENG-PCS-01-05694 | 2022-09-13 | مورد تایید است.
2 | نقطه نظر پیشین: با توجه به عدم وجود تجهيزات لازم براي جدايش نفت و آب، نمايش دو سطح مايع نياز به بازنگري دارد. |  | BK-SUR-ENG-PCS-01-05694 | 2022-09-13 | طبق آخرین تغییرات بوت و بدنه ی اصلی درام به صورت یکپارچه در نظر گرفته شده و سطوح مایع بر این اساس در نظر گرفته شده است.
3 | نحوه نمایش LG و LT روی ظرف به گونه ای باشد که سطح مایع، از نازل L2 تا L1 را پوشش دهد. |  | BK-SUR-ENG-PCS-01-05694 | 2022-09-13 | مطابق با آخرین ویرایش P&ID به همین ترتیب در نظر گرفته شده است.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05694 | 2022-09-13 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: