## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0006 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1307 |  |  | Transmital Date: 8/24/2022
Document Title: P&ID - 1st Stage Gas Compression Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1307 |  |  | Transmital Date: 8/24/2022
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0006_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقطه نظر پیشین: نهايي سازي خطوط فلر منوط به ارسال محاسبات قابل قبول مي باشد .(مفاد صورتجلسه مورخ 1401/06/19 در این خصوص مد نظر قرار گیرد) |  | BK-SUR-ENG-PCS-01-05694 | 2022-09-13 | مورد تایید است.
2 | نتایج مطالعه خواسته شده، مطابق با HAZOP Recommendation شماره 37، می بایست توسط پیمانکار گزارش گردد. |  | BK-SUR-ENG-PCS-01-05694 | 2022-07-09 | نتایج مطالعات خواسته شده پس از برگزاری جلسات Hazop برای Compressor ارایه می گردد.
3 | HAZOP Recommendation شماره 44، اعمال نشده است. |  | BK-SUR-ENG-PCS-01-05694 | 2022-07-09 | اعمال گردید.
4 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05694 | 2022-07-09 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: