## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0009 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1307 |  |  | Transmital Date: 8/24/2022
Document Title: P&ID - 2nd Stage Gas Compression Suction Drums |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1307 |  |  | Transmital Date: 8/24/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0009_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | توصیه شماره 46 از مدرک HAZOP Report for Compressor Station”" اعمال شود. |  | 1401-2294-281080 | 1401/08/03 | توصیه شماره 46 از مدرک ”HAZOP Report for Compressor Station" در مدرک P&ID - 2nd Stage Gas Compression Compressors به شماره مدرک "BK-GCS-PEDCO-120-PR-PI-0010 " اعمال شده است.
2 | باتوجه به حذف جریان Spill Back از کولر هوایی دوم (AE-2102) به ورودی Suction Drum کمپرسور دوم (V-2102) ، مدرک PFD اصلاح شده و برای این امور ارسال گردد. |  | 1401-2294-281080 | 1401/08/03 | کامنت فوق در مدرک PFD اعمال و متعاقبا ارسال می گردد.
3 | دلیل تغییر نوع شیرهای تخلیه ¾” بر روی نازل S(Utility Connection) و 2” بر روی نازل B2 (Liquid Outlet) برای V-2102 و همچنین شیر تخلیه قبل از XV-2131 از Gate Valve به Ball Valve ارائه گردد ( تغییرات نوع شیر قابل پذیرش نیست؛ در صورت وجود الزام استانداردی توضیحات لازم ارائه گردد). |  | 1401-2294-281080 | 1401/08/03 | اصلاح گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: