## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0011 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1308 |  |  | Transmital Date: 8/24/2022
Document Title: P&ID - 2nd Stage Gas Compression Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1308 |  |  | Transmital Date: 8/24/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | توصیه شماره 40 از مدرک "HAZOP Report for Compressor Station” اعمال شود. |  | 1401-2294-283491 | 1401/08/07 | در آیتم شماره 40 از مدرک "HAZOP Report for Compressor Station” در خصوص Maintenece Lock فن کولر هوایی اشاره شده که می در مدرک Data Sheet مکانیکال تجهیز فوق اعمال می گردد. |  |  | دیسیپلین مکانیک
2 | شماتیک کولر هوایی بایستی بصورت Induced Draft Type Air Cooler نمایش داده شود و شماتیک مربوط به مدرک “ Symbol and Legend for PFD and P&ID" اضافه شود. |  | 1401-2294-283491 | 1401/08/07 | اعمال گردید. |  |  | آقای روشنایی
3 | کلاس فشاری شیر BDV-2132 مورد بازنگری قرار گیرد اسناد پایه ملاک عمل قرار گیرد |  | 1401-2294-283491 | 1401/08/07 | در مدارک طراحی پایه کلاس فشاری شیر BDV-2132 در مدرک PMS(PIPING MATERIAL SPECIFICATION) به شماره مدرک "1560-BK-NCS-PI-SPC-0001-06" برابر با 600# (کلاس FS20)در نظر گرفته شده است که این کلاس خط معادل کلاس خط معادل FS00 در مدرک PIPING MATERIAL SPECIFICATION به شماره مدرک " BK-GCS-PEDCO-120-PI-SP-0001" در مدارک طراحی تفضیلی می باشد.
4 | کلاس فشاری شیر PCV-2135 در مدرک در ج گردد. |  | 1401-2294-283491 | 1401/08/07 | رجوع شود به پاسخ بند 3 فوق
5 | کلاس فشاری شیر XV-2133 با توجه به فشار جریانی عبوری از آن به 600# اصلاح گردد |  | 1401-2294-283491 | 1401/08/07 | رجوع شود به پاسخ بند 3 فوق
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: