## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0014 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1308 |  |  | Transmital Date: 8/24/2022
Document Title: P&ID - Lean Glycol Storage Tank |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1308 |  |  | Transmital Date: 8/24/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0014_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | توصیه ردیف 69 از مدرک "HAZOP Report for Compressor Station" مد نظر قرار گیرد. |  | 1401-2294-283491 | 1401/08/07 | توصیه ردیف 69 از مدرک "HAZOP Report for Compressor Station" در ویرایش قبلی مدرک اعمال شده است.
2 | مبنای انتخاب Pset برای شیرهای PRV-2161/2162 بروی جریان N2 برای Blanketing تانک TK-2102 می باید بیان گردد. |  | 1401-2294-283491 | 1401/08/07 | مبنای انتخاب بر اساس بند 6.3.4 استاندارد IPS-E-PR-360 می باشد.
3 | Pset برای شیرهای PRV-2161/2162 با فشار طراحی TK-2102 مغایرت دارد. |  | 1401-2294-283491 | 1401/08/07 | رجوع شود به پاسخ بند 2 فوق
4 | شیرهای تخلیه 3/4" بر روی نازل (Utility Connection)S برای TK_2102 از Gate Valve به Ball Valve تغییر یافته است. |  | 1401-2294-2834914 | 1401/08/07 | اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: