## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0025 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1309 |  |  | Transmital Date: 8/24/2022
Document Title: P&ID - Glycol Sump Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1309 |  |  | Transmital Date: 8/24/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همراه با ارسال ویرایش بعد محاسبات سایزینگ شیر PSV-2293 نیز ارسال گردد. |  | 1401-2294-285752 | 1401/08/07 | محاسبات در مدرک مربوطه ارسال گردیده است.
2 | در توضیحات جریان خروجی از PSV-2293 به سمت FLARE HEADER شماره P&ID مورد بررسی قرار گیرد ضمنا کلیه شماره سریال های خطوط مذکور در P&ID مبدا و مقصد می باید همسازی شود. |  | 1401-2294-285752 | 1401/08/07 | اعمال گردید.
3 | PSET مربوط به شیرهای PRV-2291 و PRV-2292 مورد بررسی و اصلاح قرار گیرد. |  | 1401-2294-285752 | 1401/08/07 | مبنای انتخاب بر اساس بند 6.3.4 استاندارد IPS-E-PR-360 می باشد.
4 | داده برگ فرآیندی مربوط به V-2107 همراه با ویرایش بعد مدرک ارسال گردد. |  | 1401-2294-285752 | 1401/08/07 | متعاقبا ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: