## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0020 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1314 |  |  | Transmital Date: 8/27/2022
Document Title: P&ID - LP Flare System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1314 |  |  | Transmital Date: 8/27/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اينكه سيال ورودي ار PID-4 sh.2 كاملا مايع مي باشد لذا اين خط مي بايست به شبكه Closed drain متصل گردد. |  | BK-SUR-ENG-PCS-01-05731 | 2022-09-20 | اعمال گردید.
2 | تمامي ورودي ها به شبكه فلر مججدا مورد بررسي قرار گيرد به عنوان نمونه تعداد و شماره خطوط دريافتي از PI-25 صحيح نمي باشد. |  | BK-SUR-ENG-PCS-01-05731 | 2022-09-20 | چک واصلاح گردید.
3 | نقطه نظر پيشين: شيب كليه خطوط و Sub-Header ها درج گردد. |  | BK-SUR-ENG-PCS-01-05731 | 2022-09-20 | اعمال گردید.
4 | نقطه نظر پيشين: نهايي سازي اين دياگرام منوط به نهايي سازي شبكه فلر و محاسبات تشعشع مي باشد. |  | BK-SUR-ENG-PCS-01-05731 | 2022-09-20 | مورد تایید است.
5 | نقطه نظر پيشين: مشخصات Blower درج گردد. |  | BK-SUR-ENG-PCS-01-05731 | 2022-09-20 | پس از دریافت اطلاعات از سازنده اضافه میگردد.
6 | پيشنهاد آيتم 101 گزارشHAZOP (مانيتورينگ فلر در CCTV و در اتاق كنترل)به صورت Note در اين مدرك ارائه گردد |  | BK-SUR-ENG-PCS-01-05731 | 2022-09-20 | اعمال گردید.
7 | پيشنهاد آيتم 104 گزارشHAZOP (اطمينان بهره برداراز بازبودن مسيرخروجي P-2201A/B )به صورت Note در اين مدرك ارائه گردد |  | BK-SUR-ENG-PCS-01-05731 | 2022-09-20 | اعمال گردید.
8 | نقطه نظر پيشين: قطر و طول استك مي بايست براساس نقطه نظرات ارائه شده در خصوص محاسبات تشعشع اصلاح گردد. |  | BK-SUR-ENG-PCS-01-05731 | 2022-09-20 | مقادیر ذکر شده طبق آخرین محاسبات و توافقات اصلاح گردیده است.
9 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-05731 | 2022-09-20 | اعمال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: