## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W008N-PEDCO-110-PR-LI-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0403 |  |  | Transmital Date: 29/12/2021
Document Title: Line List - W008N |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-0403 |  |  | Transmital Date: 29/12/2021
[5 empty] | CRS No: CRS-BK-W008N-PEDCO-110-PR-LI-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نهايي سازي اين مدرك منوط به نهايي شدن مطالعات خوردگي و به تبع آن PMS و P&ID پروژه مي باشد. |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | مورد تایید است.
2 | در صورت تاييد ذينفع اصلي امكان درنظر گرفتن كلاس 150 براي خط گودال سوزا وجود دارد. |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | مورد تایید است.
3 | فاز سيال مجددا مورد بازنگري قرار گيرد. |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | اصلاح گردید.
4 | مبدا خط شماره 162 نادرست است. |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | اصلاح گردید.
5 | شماره ارجاع شده P&ID نادرست است. |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | اصلاح گردید.
6 | شماره خط آخر با P&ID مطابقت ندارد. |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | اصلاح گردید.
7 | كامنت پاپينگ: فشار طراحي مي بايست به 207 بار نسبي تغيير يابد. |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12
8 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-00-02647 | 2022-01-12 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021